Schedule 21 (Variation Form)

This form is to be used in order to change a contract in accordance with Clause 28 of the Core Terms (Changing this Contract).

Variation Details Table

| Contract Details |  |
| --- | --- |
| This variation is between: | Northgate Interiors Ltd ("the Buyer") And Harper & Lane LLP ("the Supplier") |
| Contract name: | Legal Services Retainer ("this Contract") |
| Contract reference number: | HL-2026-0412 |
| Details of Proposed Variation |  |
| Variation initiated by: | Buyer |
| Variation number: | 1 |
| Date variation is raised: | 29 September 2026 |
| Proposed variation |  |
| Reason for the variation: | Northgate Interiors is opening a second site in Leeds in January and the employee handbook needs to cover hybrid working and the new site rules. |
| An Impact Assessment shall be provided within: | 10 days |
| Impact of Variation |  |
| Likely impact of the proposed variation: | The handbook review needs about 12 extra fee-earner days in November and December. It does not affect the quarterly policy checks already booked, but the final reports move to the end of January 2027. |
| Outcome of Variation |  |
| Contract variation: | This Contract detailed above is varied as set out in the table below. |

| Clause or deliverable | Before | After |
| --- | --- | --- |
| Schedule 2 (Scope of Services), item 4 | Quarterly policy check | Quarterly policy check and one full review of the employee handbook |
| Schedule 3 (Timetable), item 2 | Reports delivered by 15 December 2026 | Reports delivered by 31 January 2027 |

Financial variation

| Original Contract value: | £18,000 |
| --- | --- |
| Additional cost due to this Variation: | £2,750 |
| New Contract value: | £20,750 |

1  Effectiveness and Signature Requirement

This Variation must be agreed and signed by both Parties to this Contract and shall only be effective from the date it is signed by the Buyer.

2  Defined Terms

Words and expressions in this Variation shall have the meanings given to them in this Contract.

3  Continuity of Contract

The Contract, including any previous Variations, shall remain effective and unaltered except as amended by this Variation.

Buyer Signature Block

Signed by an authorised signatory for and on behalf of the Buyer

| Signature |  |
| --- | --- |
| Date |  |
| Name (in Capitals) | Dana Whitcombe |
| Address | Northgate Interiors Ltd, Unit 9, Calder Park, Wakefield WF2 7AY |

Supplier Signature Block

Signed by an authorised signatory to sign for and on behalf of the Supplier

| Signature |  |
| --- | --- |
| Date |  |
| Name (in Capitals) | Marcus Lane |
| Address | Harper & Lane LLP, 12 Albion Street, Leeds LS1 5AA |