Pay less notice

Housing Grants, Construction and Regeneration Act 1996, section 111

To (payee): Ridgeway Masonry Ltd, Unit 3, Quarry Park, Keighley BD21 4QE

From (payer): Northvale Construction Ltd, 22 Albion Street, Leeds LS1 6HX

Contract: Subcontract for the brickwork and screeds package, ref NC-HF2-SC14, dated 3 March 2026

Project: Hawthorn Fields Phase 2, Moor Road, Pudsey LS28 7RT

Payment application or payment notice this relates to: Interim payment application no. 7, dated 2 October 2026

Sum stated in that notice (the notified sum): £86,400

Due date for payment: 16 October 2026

Final date for payment: 30 October 2026

Date this notice is given: 7 October 2026

1  Notice

We give notice that we intend to pay less than the notified sum.

2  The sum we consider to be due

The sum we consider to be due on the date this notice is given is:

£66,450 excluding VAT

3  The basis on which this sum is calculated

| Item | Amount in notified sum (£) | Amount we consider due (£) | Difference (£) | Reason and how calculated |
| --- | --- | --- | --- | --- |
| Item 4.2 – brickwork (measured work) | £36,000 | £24,000 | £12,000 | 60% complete on inspection on 1 October 2026, not 90% as claimed: brickwork 60% × £40,000 = £24,000 |
| Item 6.1 – screed (defective work) | £8,500 | £5,300 | £3,200 | Screed to plots 7-9 out of tolerance; remedial work assessed at £3,200, see defects list DL-07 |
| Variation 3 | £4,750 | £0 | £4,750 | Not instructed; no variation order issued |
| Total | £86,400 | £66,450 | £19,950 |  |

Supporting documents: QS assessment dated 6 October 2026, defects list DL-07 and site photographs of 1 October 2026.

4  Payment

We will pay the sum stated in section 2 on or before the final date for payment. This notice is given no later than 5 days, as the contract requires before the final date for payment.

Signed: ______________

Name: Anita Shah

Position: Commercial Director

For and on behalf of: Northvale Construction Ltd

Date: 7 October 2026