Pay less notice
Housing Grants, Construction and Regeneration Act 1996, section 111
To (payee): Ridgeway Masonry Ltd, Unit 3, Quarry Park, Keighley BD21 4QE
From (payer): Northvale Construction Ltd, 22 Albion Street, Leeds LS1 6HX
Contract: Subcontract for the brickwork and screeds package, ref NC-HF2-SC14, dated 3 March 2026
Project: Hawthorn Fields Phase 2, Moor Road, Pudsey LS28 7RT
Payment application or payment notice this relates to: Interim payment application no. 7, dated 2 October 2026
Sum stated in that notice (the notified sum): £86,400
Due date for payment: 16 October 2026
Final date for payment: 30 October 2026
Date this notice is given: 7 October 2026
1  Notice
We give notice that we intend to pay less than the notified sum.
2  The sum we consider to be due
The sum we consider to be due on the date this notice is given is:
£66,450 excluding VAT
3  The basis on which this sum is calculated
	Item
	Amount in notified sum (£)
	Amount we consider due (£)
	Difference (£)
	Reason and how calculated

	Item 4.2 – brickwork (measured work)
	£36,000
	£24,000
	£12,000
	60% complete on inspection on 1 October 2026, not 90% as claimed: brickwork 60% × £40,000 = £24,000

	Item 6.1 – screed (defective work)
	£8,500
	£5,300
	£3,200
	Screed to plots 7-9 out of tolerance; remedial work assessed at £3,200, see defects list DL-07

	Variation 3
	£4,750
	£0
	£4,750
	Not instructed; no variation order issued

	Total
	£86,400
	£66,450
	£19,950
	


Supporting documents: QS assessment dated 6 October 2026, defects list DL-07 and site photographs of 1 October 2026.
4  Payment
We will pay the sum stated in section 2 on or before the final date for payment. This notice is given no later than 5 days, as the contract requires before the final date for payment.
Signed: ______________
Name: Anita Shah
Position: Commercial Director
For and on behalf of: Northvale Construction Ltd
Date: 7 October 2026
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