Snagging list

Project: 7 Larch Close, Otley LS21 2NE (rear extension and kitchen refit)

Contract: PDB-2026-118

Client: Gemma Archer

Contractor: Pickard Design & Build Ltd

Inspection date: 5 October 2026

Inspected by: Gemma Archer (client), Dan Pickard and Ollie Shaw (Pickard Design & Build Ltd)

Snags

| No. | Location | Description of the snag | Photo ref | Responsible | Priority | Target date | Done (date and initials) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Kitchen, north wall | Cracked tile behind hob, 2nd row | P01 | Tiler | High | 16 October 2026 |  |
| 2 | Kitchen island | Drawer front misaligned, rubs on end panel | P02 | Joiner | Normal | 16 October 2026 |  |
| 3 | Extension, rear bifold doors | Draught at bottom threshold | P03 | Contractor (door supplier) | High | 12 October 2026 |  |
| 4 | Extension ceiling | Hairline crack in plaster near rooflight | P04 | Plasterer | Cosmetic | 23 October 2026 |  |
| 5 | Utility room | Extractor fan not ducted outside, vents into void | P05 | Electrician | High | 12 October 2026 |  |
| 6 | Downstairs WC | Silicone to basin incomplete at tap end | P06 | Contractor | Normal | 16 October 2026 |  |

Total snags: 6

Items not agreed as snags: 1 item: the colour of the external render on the side wall. The contractor says it matches the agreed sample; the client disputes this until a second sample panel has been seen.

Next steps

The contractor will complete all items by 23 October 2026 and will tell the client when they are ready for re-inspection. Re-inspection is arranged for 26 October 2026 at 10am.

Agreeing this list does not mean the client accepts the work as free of defects. Defects found later can still be reported under the contract or any guarantee.

Client: Name: Gemma Archer  Signature: ______________  Date: ______________

Contractor: Name: Pickard Design & Build Ltd  Signature: ______________  Date: ______________

Sign-off on completion of snags

All items above have been completed to the client’s reasonable satisfaction, except any items listed here, which are carried forward to the date shown:

Items carried forward: ______________________  to: ______________

Client: Signature: ______________  Date: ______________

Contractor: Signature: ______________  Date: ______________